## Sheet1
重构方案分类 | 耦合点(文件:行号) | 正向信号 | 子系统 | 文件路径 | 耦合代码行号 | 匹配字面量/模式 | 备注 | 责任人 | 功能分类(大类) | 功能分类(子类) | 技术难度 | 优先级
C1-R0 移除设备名字面量门禁→查 PrivateUse1 dispatch key/能力接口 | torch/distributed/nn/api/remote_module.py:480 | P1 | Distributed | torch/distributed/nn/api/remote_module.py | 480 | "cuda" |  | 邹昌松 | 分布式·2.Pipeline/Checkpoint/通信库 | 通信库(ProcessGroup/Rendezvous/DeviceMesh) | 低
C1-R0 移除设备名字面量门禁→查 PrivateUse1 dispatch key/能力接口 | torch/distributed/tensor/_dispatch.py:414 | P1 | Distributed | torch/distributed/tensor/_dispatch.py | 414 | "cuda" |  | 邹昌松 | 分布式·1.FSDP/Shard | FSDP/DTensor/ShardedTensor补丁与分片 | 低
C1-R0 移除设备名字面量门禁→查 PrivateUse1 dispatch key/能力接口 | torch/distributed/tensor/_ops/strategy_validation.py:2111 | P1 | Distributed | torch/distributed/tensor/_ops/strategy_validation.py | 2111 | "cuda" |  | 邹昌松 | 分布式·1.FSDP/Shard | FSDP/DTensor/ShardedTensor补丁与分片 | 低
C1-R0 移除设备名字面量门禁→查 PrivateUse1 dispatch key/能力接口 | torch/fx/experimental/const_fold.py:33 | P1 | FX/Functorch/Refs | torch/fx/experimental/const_fold.py | 33 | "cuda" |  | 邹昌松 | 图模式·2.inductor+triton后端 | AOTAutograd/FX IR变换 | 低
C1-R0 移除设备名字面量门禁→查 PrivateUse1 dispatch key/能力接口 | torch/fx/passes/backends/cudagraphs.py:37 | P1 | FX/Functorch/Refs | torch/fx/passes/backends/cudagraphs.py | 37 | "cuda" | 文件名含 cuda(疑 CUDA 专属特性) | 邹昌松 | 图模式·2.inductor+triton后端 | AOTAutograd/FX IR变换 | 低
C1-R0 移除设备名字面量门禁→查 PrivateUse1 dispatch key/能力接口 | torch/jit/_script.py:993 | P1 | JIT/Autograd | torch/jit/_script.py | 993 | "cuda" |  | 邹昌松 | 图模式·1.aclgraph后端 | [旧版]JIT Fusion/ONNX Export | 低
C1-R0 移除设备名字面量门禁→查 PrivateUse1 dispatch key/能力接口 | torch/jit/_serialization.py:225 | P1 | JIT/Autograd | torch/jit/_serialization.py | 225 | "cuda" |  | 邹昌松 | 图模式·1.aclgraph后端 | [旧版]JIT Fusion/ONNX Export | 低
C1-R0 移除设备名字面量门禁→查 PrivateUse1 dispatch key/能力接口 | torch/onnx/_internal/exporter/_registration.py:58 | P1 | Other | torch/onnx/_internal/exporter/_registration.py | 58 | "cuda" |  | 邹昌松 | 图模式·1.aclgraph后端 | [旧版]JIT Fusion/ONNX Export | 低
C2-R0 去掉硬编码字面量,device 由上下文流入 | torch/_vendor/quack/_compile_worker.py:111 | P1 | Other | torch/_vendor/quack/_compile_worker.py | 111 | "cuda" |  | 邹昌松 | 图模式·2.inductor+triton后端 | NPU Triton Codegen(Triton/CUTLASS GEMM) | 低
C2-R0 去掉硬编码字面量,device 由上下文流入 | torch/_vendor/quack/autotuner.py:113 | P1 | Other | torch/_vendor/quack/autotuner.py | 113 | "cuda" |  | 邹昌松 | 图模式·2.inductor+triton后端 | NPU Triton Codegen(Triton/CUTLASS GEMM) | 低
C2-R0 去掉硬编码字面量,device 由上下文流入 | torch/_vendor/quack/trace.py:539 | P1 | Other | torch/_vendor/quack/trace.py | 539 | "cuda" |  | 邹昌松 | 图模式·2.inductor+triton后端 | NPU Triton Codegen(Triton/CUTLASS GEMM) | 低
C2-R0 去掉硬编码字面量,device 由上下文流入 | torch/distributed/rpc/server_process_global_profiler.py:181 | P1 | Distributed | torch/distributed/rpc/server_process_global_profiler.py | 181 | "cuda" |  | 邹昌松 | 分布式·2.Pipeline/Checkpoint/通信库 | RPC(远程过程调用) | 低
C5-R0+R1 torch.cuda.Stream/synchronize/etc 替为 device_interface(注册入口需公开) | torch/_inductor/kernel/vendored_templates/cutedsl/wrappers/dense_blockscaled_gemm_kernel.py:355 | P4 | Inductor | torch/_inductor/kernel/vendored_templates/cutedsl/wrappers/dense_blockscaled_gemm_kernel.py | 355 | torch.cuda.stream |  | 邹昌松 | 图模式·2.inductor+triton后端 | Inductor NPU后端(IR Lowering/Fusion/Scheduling) | 中
C5-R0+R1 torch.cuda.Stream/synchronize/etc 替为 device_interface(注册入口需公开) | torch/_inductor/wrapper_benchmark.py:502 | P4 | Inductor | torch/_inductor/wrapper_benchmark.py | 502 | torch.cuda.reset_peak_memory_stats |  | 邹昌松 | 图模式·2.inductor+triton后端 | Inductor NPU后端(IR Lowering/Fusion/Scheduling) | 中
C5-R0+R1 torch.cuda.Stream/synchronize/etc 替为 device_interface(注册入口需公开) | torch/distributed/checkpoint/filesystem.py:161 | P4 | Distributed | torch/distributed/checkpoint/filesystem.py | 161 | torch.cuda.Stream |  | 邹昌松 | 分布式·2.Pipeline/Checkpoint/通信库 | Checkpoint(分布式检查点) | 中
C5-R0+R1 torch.cuda.Stream/synchronize/etc 替为 device_interface(注册入口需公开) | torch/distributed/fsdp/_fully_shard/_fully_shard.py:595 | P4 | Distributed | torch/distributed/fsdp/_fully_shard/_fully_shard.py | 595 | torch.cuda.Stream |  | 邹昌松 | 分布式·1.FSDP/Shard | FSDP/DTensor/ShardedTensor补丁与分片 | 中
C8-R2 c10d ProcessGroup backend 字面量分支改注册表 | torch/distributed/_shard/sharded_tensor/api.py:640 | P3 | Distributed | torch/distributed/_shard/sharded_tensor/api.py | 640 | "gloo" | 存在 else/elif 非cuda分支(可能为偏好型快路,需运行性确认) | 邹昌松 | 分布式·1.FSDP/Shard | FSDP/DTensor/ShardedTensor补丁与分片 | 高
C8-R2 c10d ProcessGroup backend 字面量分支改注册表 | torch/distributed/_token_switch.py:42 | P3 | Distributed | torch/distributed/_token_switch.py | 42 | "nccl" |  | 邹昌松 | 分布式·2.Pipeline/Checkpoint/通信库 | 通信库(ProcessGroup/Rendezvous/DeviceMesh) | 高
C8-R2 c10d ProcessGroup backend 字面量分支改注册表 | torch/distributed/c10d_logger.py:65 | P3 | Distributed | torch/distributed/c10d_logger.py | 65 | "nccl" | 存在 else/elif 非cuda分支(可能为偏好型快路,需运行性确认) | 邹昌松 | 分布式·2.Pipeline/Checkpoint/通信库 | 通信库(ProcessGroup/Rendezvous/DeviceMesh) | 高